## Product Backlog
Web Photo Share Project Backlog
New Estimate of Effort Remaning as of Sprint
Item | Details (Wiki) | Priority | Status | Initial Estimate | 1 | 2 | 3
As a user, I want to register an account |  | Low
As a user, I want to login by google or yahoo account |  | Normal
As a user, I want to login to website |  | Low
As a user, I want to upload photos |  | High
As a user, I want to share my photos |  | High
As a user, I want to modify information of my photos |  | Normal
As a user, I want to delete photos by myself |  | Normal
As a user, I want to upload link photo |  | High
As a user, I want to manage albums |  | Normal
As a user, I want to search photos and albums |  | Normal
As a user, I want to send feedback to administrator |  | Low
As a user, I want to manage my profile |  | Low
As a user, I want to view photos by slideshow |  | Normal
As a admin, I want to accept/reject registration of user |  | Low
As a admin, I want to manage users |  | Low
As a admin, I want to reply feedback |  | Low
As a admin, I want to manage FAQs |  | Low
As a user, I want to have friends |  | High
Là khách thuê xe, tôi muốn đổi loại xe mà tôi đã đặt trong trường hợp thay đổi |  | Normal |  | 9.5
Là khách thuê xe, tôi muốn hủy việc đặt xe của tôi trong trường hợp thay đổi |  | Normal |  | 4

## Sprint1 Backlog
Web Photo Share Project Sprint Backlog
ID | Task | Responsible | Related Task | Status(Not Started In Progress Completed) | Hours of Work Remaining Until Completion
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Design database (8) |  |  | Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Discuss database together | All members |  | Completed
| Create query file | Canh |  | Completed
2 | Design system prototype (13) |  |  | In Progress | 11 | 11 | 6 | 6 | 6 | 2 | 2 | 2
| Drawing in paper | All members |  | Completed
| Create JSF template | Canh |  | In Progress
3 | Discuss class diagram (5) |  |  | In Progress | 4.5 | 4.5 | 4.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Create project | Chung, Nam |  | Completed
| Create JPA Entities | Chung, Nam |  | Completed
| Discuss class diagram | Chung, Nam |  | In Progress
4 | Upload photos (5) | Nhi, canh |  | In Progress | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 3 | 3 | 3
| Study file upload of primefaces | Nhi, canh |  | In Progress
| Code business | Nhi, canh |  | In Progress
| Test function | Nhi, canh |  | In Progress
5 | Upload link photos (5) |  |  | Not Started | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
Study creating form by primefaces
Code business
Test function
6 | Share photos (3) |  |  | In Progress | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4
Create security for album
| Share photos to other social networks | Cuong |  | In Progress
Test function
7 | Show photos (5) |  |  | In Progress | 4.5 | 4.5 | 4.5 | 4.5 | 9 | 9 | 2 | 2
| Show albums | Chung |  | In Progress
| Show photos | Chung |  | In Progress
| Show photo details | Cuong |  | In Progress
Test function
8 | Refactor code (5) |  |  | Not Started | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5
Suggest new codes or design patterns
Replace new codes
|  |  | Total: |  | 43.5 | 36.5 | 31.5 | 28.5 | 34 | 28.5 | 21.5 | 21.5

## Fund group
Fund name | Date | Trần Phương Nam (PN) | Trịnh Thị Nhị (TN) | Nguyễn Đình Cảnh(DC) | Nguyễn Tạ Cường(TC) | Nguyễn Trí Chung(C) | Remain persons
Reasonable absence | 2012-03-06 | 0 | 0 | 50000 | 0 | 0
Initial fund | 2012-03-08 | 30000 | 30000 | 30000 | 30000 | 30000
Violate Timebox | 2012-03-08 | 50000 | 50000 | 0 | 0 | 0
Purchase biscuits | 2012-03-08 | 0 | 0 | -8000 | -8000 | -8000
Commit error | 2012-03-12 | 0 | 0 | 0 | 0 | 0
Eat "Banh ran" | 2012-03-12 | -5000 | -5000 | 0 | 0 | -5000
Drink tea | 2012-03-12 | -2000 | -2000 | 0 | 0 | -1000
G7 | 2012-03-13 | 0 | -46000
Eating | 2012-03-15 | 0 |  | -50000
Eating | 2012-03-22 |  | -4000
Reasonable absence x3 | 2012-03-21 |  |  |  | 100000
Drink tea | 2012-03-28 | -15000
Eat "Banh ran" | 2012-03-29 | -15000
Final party | 2012-01-04 | -43000 | -23000 | -22000 | -122000 | -16000
Total |  | 0 | 0 | 0 | 0 | 0 | 0

## Members
eProject Code | RollNo | Student Name | Email | Mobile Phone | Role | Purpose of eproject | Advantages | Disavantages
3152 | A04531 |  |  |  | Scrum Team | I want to make a product which is real product. It's not a product on paper. | Good programmer. | I have to do 2 projects at the same time. I can't work overtime. I can't work fulltime
3030 | A04535 |  |  |  | Product Owner, Scrum Team | I want to get highest mark on my group. I want to understand more about scrum. | Good programmer. I can work full time. | I have a few knowledge about JSF. I can't go to work early.
3302 | A04282 |  |  |  | Scrum Team | I want to learn basic programming. I want to make a great product which I feel proud. | Normal programmer. I can work full time. | I'm not patient.
3305 | A03916 |  |  |  | Scrum Master, Scrum Team | I want our group work together more effectively, all of members will be happy after eproject. I want make a product which is good and extendable. | Good programmer. | I'm can't work fulltime and overtime. I don't have a laptop.
261 | A04230 |  |  |  | Scrum Team | I want to make a product which is as simple as possible. I want to have more knowledge about programming. | Normal programmer. I can work full time. | Sometimes, I'm busy and I can't work. Long time ago, I didn't code.
Big Problem: Our Group don't have a appropriate place to work

## Rules
Currency: 1 dep = 50,000 VND
| Rules | Fees
1 | Go daily meeting late | 1 dep
2 | Not go to work but have reason | 1 dep
3 | Not go to work with no reason | 2 dep
4 | Not help partner | 1 dep
5 | Argue with partner (have warming) | 1 dep
6 | Scrum master argue with scrum team | 2 dep
7 | Go other meeting late | 1 dep
8 | Not go to other meeting | 2 dep
9 | Not update sprint backlog everyday | 1 dep
10 | Causes of error project by committing code | 1 dep
11 | Violate Timebox (9:00 to 11:30 , 13:30 to 16:30) about 30 minutes | 1 dep
Commit Rules
1 | Update before commit
2 | Don't commit error code
3 | Update and commit everyday

## Meetings
Prepare for eproject meeting
March 1st, 2012 (2pm to 4pm at fat1)
Content
1 | Talking about our purpose of eproject (10 minutes)
2 | Talking about our advantages and disadvantages (10 minutes)
3 | Making our working schedule (15 minutes)
4 | Make our group's rules (15 minutes)
5 | Discuss about how to work together (15 minutes)
6 | Define DONE (10 minutes)
7 | Discuss about Web Photo Share together (45 minutes)

## Working Schedule
Date | Content | Nam | Canh | Nhi | Chung | Cuong
2012-03-03 | Not working
2012-03-04 | Not working
2012-03-05 | Sprint 1 Planning meeting Sprint 1 | Present | Absent | Present | Present | Present
2012-03-06 | Sprint 1 |  | Absent | Present | Present | Present
2012-03-07 | Sprint 1 |  | Present | Present | Present | Present
2012-03-08 | Sprint 1 |  | Present | Present | Present | Present
2012-03-09 | Sprint 1 |  | Present | Present | Present | Present
2012-03-10 | Not working (Overtime) |  | Present | Present | Present | Present
2012-03-11 | Not working
2012-03-12 | Sprint 1 Review meeting Retrospective meeting |  | Present | Present | Present | Present
2012-03-13 | Submit Report Sprint 2 Planning meeting |  | Present | Present | Present | Present
2012-03-14 | Sprint 2 |  | Present | Present | Present | Present
2012-03-15 | Sprint 2 |  | Present | Present | Present | Present
2012-03-16 | Sprint 2 |  | Present | Present | Present | Present
2012-03-17 | Not working (Overtime) |  | Present |  | Present
2012-03-18 | Not working
2012-03-19 | Sprint 2 |  | Present | Present | Present | Present
2012-03-20 | Sprint 2 |  | Present | Present | Present | Present
2012-03-21 | Sprint 2 | Present | Present | Present | Present | Absent
2012-03-22 | Sprint 2 Review meeting Retrospective meeting | Present | Present | Present | Present | Absent
2012-03-23 | Submit Report Sprint 3 Planning meeting | Present | Present | Present | Present | Absent
2012-03-24 | Not working (Overtime) | Present |  | Present | Present
2012-03-25 | Not working
2012-03-26 | Sprint 3 | Present | Present | Present | Present | Present
2012-03-27 | Sprint 3 | Present | Present | Present | Present | Present
2012-03-28 | Sprint 3 | Present | Present | Present | Present | Present
2012-03-29 | Sprint 3 | Present | Present | Present | Present | Present
2012-03-30 | Sprint 3 | Present | Present | Present | Present | Present
2012-03-31 | Not working
2012-04-01 | Not working
2012-04-02 | Sprint 3 Review meeting Retrospective meeting | Present | Present | Present | Present | Present
2012-04-03 | Submit Report and Code | Present | Present | Present | Present | Present
Daily meeting at 12:00 pm every working day